## Auto Constrained - Arterial Lin
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Federal Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: New Arterial Link or Interchange
Beltline Local Arterial Bridge | Beaver Street to Delta Highway | Construct new 2-lane arterial bridge over the Willamette River connecting Green Acres Road with Division Ave. Include modifications to Beltline/Delta ramps consistent with the Beltline Highway Facility Plan | ODOT, Lane County, City of Eugene | non-exempt; regionally significant; project of local AQ concern | 83000000 | 2025-2029 |  | 0.95 | 512 | minor arterial | ETSP MM-3 | incomplete
Eugene-Springfield Highway (SR-126) | at Main Street | Construct interchange | ODOT | non-exempt; regionally significant | 50000000 | 2030-2034 |  | 0 | 27 | Other Freeways and Expressways | STSP R-43
Eugene-Springfield Highway (SR-126) | at 52nd Street | Construct interchange | ODOT | non-exempt; regionally significant | 40000000 | 2025-2029 |  | 0 | 30 | Other Freeways and Expressways | STSP R-40

## Auto Constrained - Added Fwy
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range |  | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Added Freeway Lanes or Major Interchange Improvements
Randy Pape Beltline Highway | Roosevelt Boulevard to W. 11th Avenue | Add lanes on Belltine Highway and provide intersection improvements at the W. 11th Avenue and Roosevelt Boulevard intersections. | ODOT, Eugene | non-exempt; regionally significant | 28100000 | 2030-2034 |  |  | 1.1 | 312 | Other Principal Arterial | ETSP MM-20 | incomplete
Delta/Beltline Interchange |  | Interim/safety improvements; replace/revise existing ramps; widen Delta Highway bridge to five lanes | ODOT | non-exempt; regionally significant | 20000000 | 2020-2024 |  |  | 0.25 | 638 | Other Freeways and Expressways | ETSP MM-3 (part) | Construction will be completed in 2021
Eugene-Springfield Highway (OR 126) | @ Mohawk Boulevard Interchange | Add lanes on ramps | non exempt; regionally significant | ODOT | 2000000 | 2030-2034 | 3066559 | 3464862 | 0.68 | 821 | Other Freeways and Expressways |  | Future operational deficiencies at this interchange are discussed in the Springfield TSP (2020) but no projects are identified. It is also discussed in the ODOT OR126E Expressway Management Plan (2006).

## Auto Constrained - Arterial Cap
Name | Geogrpahic Limits | Description | Air Quality Status | Primary Jurisdiction | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Range | Length | RTP # | Federal Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Arterial Capacity Improvements
Main Street | at 48th Street | Traffic control improvements | Non-Exempt; Regionally significant | Springfield | 300000 | 2025-2029 |  | 0 | 69 | Other Principal Arterial |  | Being studied further with Main Street Safety Project
Main Street | at Mountaingate Drive | Traffic control improvements - signal | Non-Exempt; Regionally significant | Springfield | 900000 | 2025-2029 |  | 0 | 75 | Other Principal Arterial | R-48 | Being studied further with Main Street Safety Project
42nd Street | at Marcola Road | Roundabout | Non-Exempt | Springfield | 2800000 | 2020-2024 |  | 0 | 712 | Minor Arterial | R-32 | May be incorporated into Hb2017 funded 42nd St project
Harlow Road | at Pheasant Blvd | Traffic control improvements | Non-Exempt | Springfield | 500000 | 2030-2034 |  | 0 | 744 | Minor Arterial |  | Incomplete
Gateway Street | at Harlow Road | Traffic control improvements | non-exempt; regionally significant | Springfield | 2910000 | 2030-2034 |  | 0.5 | 785 | Minor Arterial |  | Incomplete
Gateway/ Beltline Rd Intersection Improvements | International Way to Postal Way | Improve intersections and realign Gateway | non-exempt; regionally significant; possibly local project of AQ concern | Springfield | 20000000 | 2025-2029 |  | 0.9 | 789 | Other Freeways and Expressways | R-50, S-1 | Incomplete
Q Street Intersection Improvements | Intersection of Q Street and 5th | Intersection improvements - Construct right turns to the eastbound and northbound approachs or a roundabout. | non-exempt | Springfield | 550000 | 2030-2034 |  | 0.5 | 828 | Minor Arterial | R-11 | Incomplete
Centennial Boulevard | @ 28th Street | Construct Roundabout | non-exempt | Springfield | 1800000 | 2035-2040 |  | 0 | 924 | Minor Arterial | R-33 | Incomplete
Centennial Boulevard | @ 21st Street | Traffic control improvements | non-exempt | Springfield | 290000 | 2035-2040 |  | 0 | 927 | Minor Arterial |  | Incomplete
S 42nd Street at Daisy Street | S. 42nd St/ Daisy Street | Traffic control improvments - Construct a traffic signal or a roundabout | non-exempt | Springfield | 1800000 | 2020-2024 |  | 0 | 951 | Minor Arterial | R-38 | In progress - horizontal design complete, funding secured, construction in next few years
Gateway Street | International Way to UGB | Construct 5 lane cross section | non-exempt | Springfield | 950000 | 2025-2029 |  | 0.63 | 704 | Minor Arterial | R-2 | Incomplete
42nd Street | Marcola Road to RR Tracks | Modify to 3 lane cross section with traffic controls at Marcola Rd and the OR126 westbound ramps | non-exempt | Springfield | 6000000 | 2020-2024 |  | 1.05 | 713 | Minor Arterial | R-36 | Funded by HB2017, engineering estimated to start in 2023 I believe
Daisy Street | @ Bob Straub Parkway | Traffic control improvements or undercrossing of Bob Straub Parkway | non-exempt | Springfield | 3000000 | 2030-2034 |  | 0 | 32 | Minor Arterial | R-44 | Incomplete
Franklin Boulevard | I-5 to RR Tracks south of Franklin Blvd/McVay Hwy | Multimodal urban standards and intresection control improvements | non-exempt; regionally significant | Springfield | 35000000 | 2020-2024 |  | 1.29 | 830 | Other Principal Arterial | R-13 | Phase 1 complete, Phase 2 in design, future phases and construction funding TBD
McVay Hwy | @ East 19th Ave | 2 lane roundabout | non-exempt | Springfield | 2500000 | 2025-2029 |  | 0 | 898 | Minor Arterial | R-19 | Incomplete
McVay Hwy | East 19th Avenue to I-5 | Construct 2 or 3 lane cross-section as needed with sidewalks, bicycle facilities and transit facilities consistent with Main Street/McVay Hwy Transit Feasibility Study and Springfield TSP project T-3. | non-exempt | Springfield | 47000000 | 2030-2034 |  | 1.34 | 899 | Minor Arterial | R-20 | Incomplete - applying for funding to do initial corridor design work, some development in area may build portions in the next few years, but unlikely to have entire corridor project completed until horizon years shown.
Marcola Road | @ 19th Street | Construct right-turn lane on westbound approach or a roundabout | non-exempt | Springfield | 320000 | 2020-2024 |  | 0 | 722 | Minor Arterial | R-30 | Incomplete - planning to do intersection analysis soon to determine design concept
28th Street | @ Marcola Road | Construct a roundabout | non-exempt | Springfield | 1900000 | 2030-2034 |  | 0 | 723 | Minor Arterial | R-31 | Incomplete
W. 11th Avenue | Green Hill Road toTerry Street | Upgrade to 5-lane urban facility | non-exempt; regionally significant | ODOT, Eugene | 12300000 | 2030-2034 |  | 1 | 333 | Other Principal Arterial | MM-14 | This project is not currently funded. This section of roadway is included in the OR126: Veneta-Eugene NEPA sudy, which will be completed in 2021.
Martin Luther King Jr. Blvd. | Leo Harris Parkway West to Centennial Loop | Add center turn lane on Martin Luther King Jr. Blvd. | Exempt / Safety - adding medians | Eugene | 6700000 | 2024-2028 |  | 0.21 | 602 | Minor Arterial | MM-8 | incomplete
Barger Drive | West of Primrose Street to where the street widens to two lanes in each direction west of Randy Papé Beltline Highway | Widen Barger Drive to provide a second through lane in each direction | non-exempt | Eugene | 1900000 | 2024-2028 |  | 0.14 | 497 | Minor Arterial | MM-21 | incomplete
Franklin Blvd. | Alder Street to Walnut Street | Upgrade to multiway blvd with 2 vehicular lanes in each direction, two EmX lanes, and a planted median | non-exempt; regionally significant; possibly local project of AQ concern | Eugene | 27700000 | 2020-2024 |  | 1 | 119 | Other Principal Arterial | MM-19 | incomplete

## Auto Constrained - New Collecto
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Range | Length | RTP # | Jurisdictional Project # | Federal Functional Class | Project Status? (Completed, incomplete, etc.)
Project Category: New Collectors
Riverbend Drive | Extend to International Way | Construct 3-lane cross section with sidewalks and bike lanes | Springfield | non-exempt | 1600000 | 2020-2024 |  | 0.19 | 715 | R-5 | Major Collector | Incomplete
Improvements to serve Riverbend Area | Baldy View Lane, McKenzie-Gateway Loop and Off-Street Path Connections | Improve Baldy View Lane, construct a McKenzie-Gateway Loop connector/new collector and construct off-street path connections. See Springfield 2035 TSP Figure 6. | Springfield | non-exempt | 10200000 | 2030-2034 |  | 0.86 | 756 | R-6 | Collector | Incomplete
79th Street | Thurston Road to Main Street | New 2 lane collector | Springfield | non-exempt | 8200000 | 2035-2040 |  | 0.37 | 18 | R-49 | Minor Collector | Incomplete
Improvements within Jasper-Natron Area | Jasper-Natron Area between Bob Straub Parkway, Jasper Road and Mt. Vernon Road | Construct multiple roadways to serve planned development.See Springfiled 2035 TSP Figure 6. | Springfield | non-exempt | 67000000 | 2030-2034 |  | 1.35 | 33,36, 39, 42, 45, 48, 51, 57 | R-45 | Collector | In progress as development occurs, R-45 was adjusted with 2020 Springfield TSP update and RTP needs to be consistent. RTP #57 looks as if it needs amending on the map.Need to look to City of Springfield, Lane County, and the Webb property agreement regarding Bob Straub Parkway access.
New Collector | Bob Straub Parkway to Mountaingate Drive and Future Local | Construct a new collector with a three-lane cro-section with sidewalks and bicycle facilities | Springfield | non-exempt | 4300000 | 2020-2024 |  | 1.03 | 81 | R-46 | Major Collector | Incomplete - update for consistency with 2020 Springfield TSP update
South 54th Street | Main Street to Daisy Street | New 2-lane collector | Springfield | non-exempt | 960000 | 2040-2045 |  | 0.28 | 87 | R-41 | Minor Collector | Incomplete, bike/ped path built in 2019. Move to illustrative to match 2020 Springfield TSP update.
19th Street | Hayden Bridge Road to Yolanda Avenue | Extend existing street as 2-lane collector | Springfield | non-exempt | 2400000 | 2030-2034 |  | 0.33 | 703 | R-24 | Minor Collector | Incomplete
V Street | 31st Street to Marcola Road | New 2 to 3-lane collector | Springfield | non-exempt | 9000000 | 2020-2024 |  | 0.65 | 777 | R-28 | Collector | Incomplete - initial phases of residential subdivision is being built.
Yolanda Avenue | 31st Street to 35th Street | Construct Yolanda Avenue from 31st Street to 33rd Street with sidewalks and bicycle facilities, add sidewalks and bicycle facilities from 33rd Street to 35th Street | Springfield | non-exempt | 9900000 | 2030-2034 |  | 0.2 | 783 | R-27 | Minor Collector | Incomplete
North Gateway Collector | Maple Island Road/ Royal Caribean Way to International | New 2-3 lane collector | Springfield | non-exempt | 4300000 | 2025-2029 |  | 0.63 | 798 | R-1 | Collector | Incomplete
Franklin Riverfront Collector | Franklin Blvd/McVay to west portion of Franklin riverfront | Collector to serve Glenwood redevelopment area along riverfront north of Franklin Blvd. | Springfield | non-exempt | 7700000 | 2020-2024 |  | 0.7 | 897 | R-12 | Collector | Incomplete
48th Street | Aster Street to Daisy Street | Extend South 48th Street with a two-lane cross-section with a parallel multi-use 12-foot wide path and roundabout intersection treatment at Daisy Street and South 48th Street | Springfield | non-exempt | 3600000 | 2025-2029 |  | 0.3 | 901 | R-39 | Major Collector | Incomplete - should description be amended to reflect multi-use path for bike/ped element and more closely reflect TSP?
New Collector | Game Farm Road East to International Way | Construct new 3- lane collector with sidewalks and bicycle facilities | Springfield | non-exempt | 6300000 | 2030-2034 |  | 0.18 | 707 | R-3 | Major Collector | Incomplete
Maple Island Road | Game Farm Road/Deadmond Ferry Road to Beltline Road | Extend Maple Island Road with a 2-lane cross-section with sidewalk, bicycle facilities, intersection at Beltline | Springfield | non-exempt | 3100000 | 2020-2024 |  | 0.11 | 706 | R-4 | Minor Collector | Incomplete
New Collector | South of Kruse Way and east of Gateway Road | Construct new collector | Springfield | non-exempt | 3100000 | Beyond 20 yr |  | 0.19 | 705 | R-7 | Collector | Incomplete - this is on the Springfield TSP Beyond 20-Year list. Should it be moved to illustrative? Please move it if so.
New Collector | Laura Street - Pioneer Parkway | Construct new 3-lane collector with sidewalks and bicycle facilities in or near the EWEB powerline corridor with a right-in/right-out intersection at Pioneer Parkway; In the Springfield TSP, PB-7 is required to serve as sidewalk and bikeway | Springfield | non-exempt | 3300000 | 2030-2034 |  | 0.12 | 786 | R-9 | Collector | Incomplete
Centennial Boulevard/ Industrial Avenue | 28th Street to 35th Street | Extend with a 3-lane cross-section | Springfield | non-exempt | 9500000 | 2030-2034 |  | 0.5 | 924 | R-34 | Major Collector | Incomplete
Commercial Avenue | Extend between 42nd Street and 48th Street and a north/south extension to serve development to the north between 42nd and 48th (see TSP map) | Extend with a 3-lane cross-section | Springfield | non-exempt | 19000000 | 2035-2040 |  | 0.84 | 19 | R-37 | Major Collector | Incomplete
New Collector | Holly Street - South 48th Street to South 57th Street | Construct new collector with 2-lane cross-section with sidewalks and bicycle facilities | Springfield | non-exempt | 5300000 | 2025-2029 |  | 0.94 | 22 | R-42 | Minor Collector | Partially complete - need to make consistent with 2020 Springfield TSP amendments.
Mallard Avenue | Gateway Street to Oriole Street | Construct new 2-lane collector | Springfield | non-exempt | 3000000 | 2035-2040 |  | 0.18 | 709 | R-8 | Minor Collector | Incomplete
Q Street | @ Laura Street | Interchange Area improvements | ODOT, Springfield | non-exempt; not regionally significant | 1600000 | 2025-2029 |  | 0 | 717 | R-10, S-3 | Major Collector | Incomplete
W. 13th Avenue (Future Collector E) | Bertelsen Road to Dani Street | New major collector | Eugene | non-exempt | 3600000 | 2020-2024 |  | 1 | 318 | UD-8 | Major collector | incomplete
Colton Way Extension (Future Collector F) | Royal Avenue to Legacy Extension | New major collector | Eugene | non-exempt | 3700000 | 2025-2029 |  | 0.7 | 429 | UD-6 | Major collector | incomplete
Legacy Extension (Future Collector H) | Avalon Street to Roosevelt Blvd | New major collector | Eugene | non-exempt | 17500000 | 2025-2029 |  | 0.5 | 435 | UD-5 | Major collector | incomplete
Future Collector J | Awbrey Lane to Enid Road | New major collector | Eugene | non-exempt | 7400000 | 2030-2034 |  | 0.8 | 441 | UD-1 | Major collector | incomplete
Gilham-County Farm Connection | Gilham to County Farm Road | New neighborhood collector | Eugene | non-exempt | 2800000 | 2020-2024 |  | 0.7 | 651 | UD-3 | Minor Collector | incomplete
Shadowview Road | Shadowview Road to Coburg Road via Spectrum Avenue | Extend neighborhood collector with two travel lanes and sidewalks on both sides | Eugene | non-exempt | 3200000 | 2020-2024 |  | 0.3 | 603 | UD-4 | Minor Collector | incomplete
Crow Road/West 11th Avenue/Pitchford area | Crow Road/West 11th Avenue/Pitchford area | Construct collectors and other facilities within Crow Road/West 11th Avenue/Pitchford area needed to serve future development | Eugene | non-exempt | 21300000 | 2025-2029 |  | 1.3 | 333 | UD-7 | Collectors | incomplete

## Auto Constrained - Urban Stnds
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2021) | Estimated Year of Construction (4-Year Window) | Year of Construction Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Urban Standards
Game Farm Road South | Mallard Road to Harlow Road | Upgrade to 2-lane urban facility | Lane County, Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 4100000 | 2030-2034 |  | 0.93 | 737 | Local | STSP-US-1; LCTSP-50 | Incomplete
Hayden Bridge Road / 23rd St | 19th Street to Marcola Rd | Reconstruct to 2-lane urban facility | Lane County, Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 12000000 | 2030-2034 |  | 1.78 | 747 | Minor Collector | R-25 | Incomplete
31st Street | Hayden Bridge Road to U Street | Upgrade to 2 lane urban facility | Lane County, Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 3800000 | 2030-2034 |  | 0.58 | 765 | Minor Collector | STSP-R-29, LCTSP-6 | Partially in progress with Marcola Meadows development and City Filling the Gaps sidewalk infill project south of EWEB multiuse path
Laura Street | Old Laura Street to Scotts Glen Drive | Widen to 3-lane urban facility | Lane County, Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 1575000 | 2020-2024 |  | 0.4 | 750 | Major Collector | US-2 | Incomplete - if City approves project in CIP in early 2021, could pair with Lane Co funded project to the north. This time frame is hopeful, depending on funding approval.This project name is different than Springfield TSP US-2. US-2 is on the beyond 20-yr list, so if this is supposed to be that same project then it should be moved to illustrative. It is unclear which project this is. Time frame revision is for OR 126B highway on-ramp to Scotts Glen Drive (city owned section)
Aspen Street | Centennial Boulevard to West D Street | Change Aspen Street to a two-lane cross-section with sidewalks and bicycle facilities | Lane County, Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 2800000 | 2030-2034 |  | 0.44 | 809 | Minor Collector | STSP-US-3, LCTSP-11 | Incomplete
48th Street | Main Street to G Street | Upgrade to a two-lane urban facility. Springfield TSP PB-55 is required to serve as sidewalk and bikeway. | Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 600000 | 2025-2029 |  | 0.48 | 3 | Major Collector | US-16 | Incomplete - should description more closely reflect TSP?
52nd Street | OR 126E to G Street | Upgrade to a two-lane urban facility. Springfield TSP PB-55 is required to serve as sidewalk and bikeway. | Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 250000 | 2020-2024 |  | 0.2 | 6 | Major Collector | US-18 | Incomplete - should description more closely reflect TSP?
G Street | 48th Street to 52nd Street | Upgrade to a two-lane urban facility. Springfield TSP PB-55 is required to serve as sidewalk and bikeway. | Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 370000 | 2020-2024 |  | 0.31 | 54 | Major Collector | US-17 | Incomplete - should description more closely reflect TSP?
Thurston Road | Weaver Road to UGB | Upgrade to 3-lane urban facility with bike facilties and sidewalks | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 4800000 | 2035-2040 |  | 0.61 | 98 | Minor Collector | US-14 | Incomplete
28th Street | Centennial Boulevard to Main Street | Widen/ provide sidewalks and bike lanes; provide intersection and signal improvements at Main Street | Springfield | non-exempt | 4300000 | 2030-2034 |  | 0.7 | 909 | Major Collector | US-5 | Incomplete
35th Street | Olympic Street to Commercial Avenue | Change 35th Street to a three-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 3600000 | 2020-2024 |  | 0.46 | 918 | Major Collector | US-8 | Incomplete
Commercial Avenue | 35th Street to 42nd Street | Modify Commercial Avenue to a three-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 4500000 | 2025-2029 |  | 0.81 | 933 | Major Collector | US-9 | Incomplete - a few ADA ramps near very east end by 42nd St were installed as part of pavement bond measure project.
S. 28th Street | Main Street to South F Street | Modify to 3-lane cross-section with sidewalks and bicycle facilities. The South 28th Dust Mitigation project will build South F Street to city limits with a multiuse path. | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 6000000 | 2020-2024 |  | 0.67 | 945 | Major Collector | US-6 | Incomplete - S. 28th Dust Mitigation project will built S. F St to city limits with a multiuse path. Perhaps description should be updated to reflect this?
21st Street | D Street to Main Street | Modify 21st Street to a three-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 2300000 | 2030-2035 |  | 0.2 | 962 | Minor Collector | US-4 | Incomplete
36th Street | Commercial Avenue to Main Street | Change 36th Street to a 3-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 3000000 | 2035-2040 |  | 0.47 | 920 | Minor Collector | US-10 | Incomplete
Clearwater Lane | South of Jasper road within the Springfield UGB | Modify and expand Clearwater Lane with a cross-section to include sidewalks and bicycle facilities | Lane County, Springfield | Exempt - Safety- widen lanes/ resurfacing/; Air Quality -bike and ped facilities | 470000 | 2025-2029 |  | 0.11 | 925 | Local | US-11 | Incomplete
Mallard Avenue | Oriole St. to Game Farm Road | Change to a 2-lane cross section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 1500000 | 2020-2024 |  | 0.31 | 710 | Local (current) | Portion of R-8 | Incomplete
East 17th Avenue | Glenwood Blvd. to Henderson Ave. | Change East 17th Avenue to a 3-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 1900000 | 2030-2034 |  | 0.52 | 826 | Minor Collector | R-16 | Incomplete
Henderson Avenue | Franklin Boulevard to East 19th Avenue | Modify Henderson Avenue with a 3-lane cross-section with sidewalks and bicycle lanes | Springfield, Lane County | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 3400000 | 2035-2040 |  | 0.39 | 827 | Local (current) | STSP-R-17, LCTSP-3 | Incomplete
East 19th Avenue | Henderson Avenue to McVay Hwy | Change East 19th Avenue to a 3-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 3500000 | 2030-2034 |  | 0.49 | 828 | Minor Collector | R-18 | Incomplete
Yolanda Avenue | 23rd Street to 31st Street | Modify Yolanda Avenue to a 2-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 460000 | 2025-2029 |  |  | 784 | Minor Collector | R-26 | Partially complete (bike lanes added from 23rd to the east for a segment, sidewalk added north side from 23rd to 27th)
Bertelsen Road | 18th Avenue to Bailey Hill Road | Upgrade to minor arterial standards with two travel lanes, bike lanes, sidewalks on both sides, and planting strips | Eugene | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 3900000 | 2020-2024 |  | 0.6 | 315 | Minor Arterial | MM-16 | incomplete
Bailey Hill Road | Warren St to Eugene UGB | Construct to eugene's minor arterial standards, including two travel lanes, center turn lane, and bike lanes, planter strip, and sidewalks on both sides | Eugene, Lane County | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 9200000 | 2020-2024 |  | 1.6 | 343 | Minor Arterial | ETSP-UD-22; LCTSP-15 | incomplete
Bethel Drive | Highway 99 to Roosevelt Blvd | Upgrade to 2-lane urban facility | Eugene | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 11800000 | 2025-2029 |  | 1.68 | 414 | Minor Collector | MM-13 | incomplete
Royal Avenue | Green Hill Road to Terry Street | Upgrade to 3-lane urban facility | Eugene | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 11200000 | 2020-2024 |  | 1.01 | 481 | Minor Arterial | UD-20 | incomplete
Jeppesen Acres Road | Gilham Road to Providence Street | Upgrade to 2-lane urban facility | Eugene | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 3900000 | 2016-2019 |  | 0.7 | 670 | Minor Collector | MM-15 | incomplete
Hunsaker Lane / Beaver Street | River Road to Division Avenue | Upgrade to 2-lane urban facility | Lane County, Eugene | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 9300000 | 2020-2024 |  | 1.14 | 527 | Major Collector | ETSP MM-11 | incomplete
Wilkes Drive | River Road to River Loop 1 | Upgrade to 3-lane urban facility | Lane County, Eugene | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 7000000 | 2025-2029 |  | 0.93 | 554 | Major Collector | ETSP UD-14 | incomplete
North Gilham Road | Ayres Road to Ashbury Drive | Upgrade to 2-lane urban facility | Eugene, Lane County | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 1500000 | 2020-2024 |  | 0.3 | 662 | Minor Collector | ETSP-UD-18; LCTSP-52b | incomplete
County Farm Road | North-to-South Section | Upgrade to 3-lane urban facility | Lane County, Eugene | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 4400000 | 2020-2024 |  | 0.62 | 631 | Major Collector | MM-12 | incomplete
County Farm Road | West-to-East Section | Upgrade to 2-lane urban facility | Eugene | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 3200000 | 2025-2029 |  | 0.53 | 632 | Major Collector | UD-19 | incomplete
Goodpasture Island Road | Delta Highway to Happy Lane | Upgrade to 2-lane urban facility | Eugene | Exempt - Safety- widen lanes/ resurfacing; Air Quality -bike and ped facilities | 163000 | 2030-2034 |  | 0.19 | 664 | Minor Arterial | PB-304; PB-305 | incomplete (we constructed sidewalk on one side)
Awbrey Lane | Prairie Road to Highway 99 | Upgrade Awbrey Lane consistent with major collector standards, including two travel lanes with bike lanes, planting strip, and sidewalks on both sides | Eugene, Lane County |  | 8700000 |  |  | 1.3 |  |  | ETSP-UD-9; LCTSP-12
Dillard Road | 43rd Ave to the Eugene UGB | Upgrade Dillard Rd consistent with major collector standards | Eugene |  | 8100000 |  |  | 1.4 |  |  | UD-23
Fox Hollow Road | Donald Street to the UGB | Upgrade Fox Hollow Rd consistent with major collector standards | Eugene, Lane County |  | 5700000 |  |  | 0.9 |  |  | ETSP-UD-24; LCTSP-48 | Lane County document says estimated cost is $5.4M
Gilham Road | Ashbury Drive to Mirror Pond Way | Construct sidewalk on the west side of Gilham Road | Lane County, Eugene |  | 272000 | [5 empty] | LCTSP-52a; | Check Eugene's TSP for this project

## Auto Constrained - Study
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2021) | Estimated Year of Construction (4-Year Window) | Year of Construction Range | Length | RTP # | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Study
OR126E (Expressway) at 52nd St and Main St | 52nd to Main | Interchange Area Management Plans | ODOT, Springfield |  | 250000 | 2025-2029 |  | 1.5 | 96 | STSP R-40, R-43 | Phase 3 of the 2006 Expressway Management Plan was never completed. It would have included IAMPs.
OR126 Expressway | I-5 to Main | Facility Plan | ODOT, Springfield |  | 750000 | 2030-2034 |  | 6.5 | 835 | S-2 | Incomplete | An expressway management plan was prepared in 2006. This would be a more detailed update.
Main Street/Highway 126 | I-5 to UGB | Access management plan | Springfield, ODOT |  | 150000 | 2020-2024 |  | 6 | 838 |  | In Progress - Main Street Safety Project Facility Plan. | Emma's comment is to the left, however, Bill Johnston deleted this project off his list... check in with both
Beltline Highway/Gateway | See TSP Map, Project S-1 | Study to reassess Gateway/Beltline Phase 2 | Springfield, ODOT |  | 800000 | 2020-2024 |  | 0.36 | 608 | S-1 | Incomplete
Pioneer Parkway/Q Street/Laura Street | See TSP Map, Project S-3 | Circulation study to improve safety, access and capacity | Springfield, ODOT |  | 300000 | 2025-2029 |  | 0.35 | 718 | S-3 | Incomplete
Main Street (OR126B) | 5th Street to 15th Street | Study a new crossing of OR 126 between 5th Street and 15th Street | Springfield, ODOT |  | 200000 | 2035-2040 |  | 0.79 | 823 | S-4 | Incomplete
Centennial Boulevard | Prescott Lane to Mill Street | Operational improvements study | Springfield |  | 100000 | 2030-2034 |  | 0.29 | 818 | S-5 | Incomplete
Pioneer Parkway | @ Centennial Boulevard | Intersection study to improve pedestrian safety | Springfield |  | 75000 | 2020-2024 |  | 0 | 849 | S-6 | Incomplete
Centennial Boulevard | Mohawk Boulevard to Pioneer Parkway | Operational improvements study | Springfield |  | 75000 | 2020-2024 |  | 1.08 | 819 | S-7 | Incomplete
Mohawk Boulevard/Olympic Street/18th Street/Centennial Triangle | Mohawk Boulevard/Olympic Street/18th Street/Centennial | Study safety and operational improvements | Springfield |  | 100000 | 2020-2024 |  | 0.9 | 916 | S-8 | Incomplete
Bridge Study | Walnut/W. D to Franklin Blvd | Study a new bridge | Springfield |  | 750000 | 2035-2040 |  | 0.28 | 815 | S-9 | Incomplete
Main Street/South A Street | Mill Street to 21st Street | Study improvements | Springfield |  | 150000 | 2020-2024 |  | 2.98 | 824 | S-10 | Partially in Progress - Main-McVay Transit Study.
Glenwood Industrial Area | See Springfield TSP Map, Project S-11 | Refinement study | Springfield |  | 150000 | 2030-2034 |  | 0.82 | 829 | S-11 | Incomplete
Pedestrian/Bicycle bridge | Between Glenwood and Dorris Ranch | Study a new pedestrian bicycle bridge | Springfield |  | 750000 | 2035-2040 |  | 0.08 | 831 | S-12 | Incomplete
Main Street (OR126B) | 20th St to 72nd St | Facility Plan | Springfield, ODOT |  | 1000000 | 2018-2022 |  | 2.23 | 917 | S-13 | In Progress - Main Street Safety Project Facility Plan. | Springfield Main Street Safety Project. Main Street west of Bob Straub Parkway is OR126B (Business).
East/west connectivity | S. 28th Street to S. 32nd street | Study east/west connectivity | Springfield |  | 100000 | 2025-2029 |  | 0.33 | 918 | S-14 | Incomplete
OR 126 | Near Thurston High School | Study a new crossing of OR 126 near Thurston High School | Springfield, ODOT |  | 200000 | 2025-2029 |  | 0.32 | 26 | S-15 | Incomplete
South of OR 126 and Jessica Street | See TSP Map, Project S-16 | Connectivity Study | Springfield |  | 100000 | 2030-2034 |  | 1.89 | 31 | S-16 | Incomplete
River Crossings | Along the Willamette River | Study ways to increase capacity over the Willamette River to address bridge crossing congestion issues. | Eugene |  | 100000 | 2025-2029 |  |  |  | ETSP S-4
Oak/Pearl and Hilyard/Patterson | Downtown to South Eugene | Evaluate north/south circulation options on the Oak/Pearl and Hilyard/Patterson Streets couplets. | Eugene |  | 100000 |  |  | 5.49 | 210 | ETSP S-3 | Send to Rob
I-105 off-ramp | I-105 at 6th Avenue | Analyze options to address weaving, operational and safety considerations at the I-105 southbound off-ramp onto 6th Avenue | ODOT, Eugene |  | 100000 | 2025-2029 |  | 0.44 | 102 | ETSP S-8
Northwest Expressway/Beltline |  | Study how to provide intersection improvements at the Northwest Expressway and Randy Pape Beltline Highway ramp termini intersections. | ODOT, Eugene, Lane County |  | 100000 | 2025-2029 |  | 0.35 | 557 | ETSP S-9
Green Hill Road | Airport Road to West 11th Avenue | Corridor Study for bike/ped access & safety | Lane County, Eugene |  | 500000 |  |  | 4.27 | 485, 454 | LCTSP-56a | LC wants the MPO to fund this
30th Avenue | I-5 to University St | Study to improvbe bicycle and pedestrian access and safety through the 30th Ave corridor between Eugene and the LCC basin, to include a review of off-road conidtions | Lane County, Eugene |  | 250000 | 2016-2019 |  | 3.14 | 211 | LCTSP-4 | Obtained MPO grant funding to commence study in fall 2019. There have been multiple bicycle and pedestrian fatalities.
Beltline Line Highway | River Rd to Delta Highway | Envrionmental Study | ODOT |  | 2000000 | 2018-2021 |  | 3.46 | 555 |  | Environmental study will be completed in 2021. Will not proceed with design until construction funding is identified.
Coburg Freight Connector Study | North of the city of Coburg between Coburg Road and I-5 | Study to determine alignment for a new east-west freight route connection between Coburg Rd and I-5, north of the city of Coburg | Lane County, Coburg, ODOT |  | 250000 |  |  |  |  | LCTSP-29
Goshen North Connector Study | McVay Highway to Goshen limits | Implement a study to identify the location of a road that provides Goshen Regional Employment Area Transitioner connectivity to and from Goshen to the north. | Lane County |  | 415000 |  |  |  |  | LCTSP-54

## Auto Constrained - TOD
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Range |  | Length | RTP # | Project Status?
Project Category: Transit Oriented Development Implementation
Planning | Various Locations | Planning for implementation of Key Corridor/Mixed Use development | Eugene, Springfield | exempt - Other - Planning and Technical Studies | 6200000 | 2016-2019 | 6200000 | 6794659 |  |  | Incomplete
Eugene Key Corridor Infrastructure Funding | Various Locations | Differential Nodal Development Infrastructure Cost* | Eugene |  | 2500000 | 2020-2024
8th Avenue | High Street to Jefferson Street | Convert 8th Avenue to a two-way street with protected bike lanes and streetscape improvements. | Eugene | non-exempt | 3200000 | 2020-2024 |  |  |  | MM-22

## Auto Illustrative - New Arteria
Name | Geographic Limits | Description | Primary Jurisdiction | AQ Status | Estimated Cost (2021) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)

## Auto Illustrative - New Collect
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2020) | Estimated Year of Construction (4-Year Window) | Year of Construction Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: New Collector Link
New Collector | Pioneer Parkway to South 2nd Street | Construct a new collector between Pioneer Parkway and South 2nd Street | Springfield | non-exempt | 700000 | 2035-2040 |  | 0.14 | 910 | Minor Collector | R-21 | Incomplete
South 14th Street Extension | South A Street to south of the Union Pacific Railroad mainline | Extend South 14th Street south of the Union Pacific Railroad mainline with a 3-lane cross-section with sidewalks and bicycle facilities | Springfield | non-exempt | 1300000 | 2035-2040 |  | 0.13 | 825 | Minor Arterial | R-22 | Incomplete
New Collector - South B Street | South 5th Street to 14th Street | Extend South B Street with a 3-lane cross-section with sidewalks and bicycle facilities | Springfield | non-exempt | 7500000 | 2035-2040 |  | 0.55 | 913 | Minor Collector | R-23 | Incomplete
South 28th Street | South F Street to South M Street | Modify South 28th Street to a 3-lane cross-section with sidewalks and bicycle facilities | Springfield | Exempt - Safety- widen lanes/ resurfacing/ add medians; Air Quality -bike and ped facilities | 5300000 | 2035-2040 |  | 0.55 | 919 | Major Collector | US-7 | Incomplete - map needs to be adjusted to match project limits, unless the geographic limits are meant to be S. F Street to UGB? Something needs to be adjusted to make project list and map consistent. Springfield TSP US-7 is "South F Street to South M Street."

## Auto Illustrative - Art Cap
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2020) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Federal Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Arterial Capacity Improvements
42nd Street at Highway 126 Westbound Ramp | 42nd St at OR126E | Traffic control and other improvements at interchange | Springfield, ODOT | non-exempt | 500000 | 2035-2040 |  | 0 | 799 | Minor Arterial | R-35 | Incomplete
Glenwood Blvd | I-5 to Franklin Blvd. | Convert Glenwood Blvd. from three-lane to five-lane cross-section | Springfield | non-exempt | 2210000 | 2035-2040 |  | 0.5 | 836 | Minor Arterial | R-15 | Incomplete
Bob Straub Parkway | Mt. Vernon Road to the Springfield UGB | Change Bob Straub Parkway to a three-lane cross-section with sidewalks and bicycle facilities | Lane County, Springfield | Exempt - Safety- widen lanes/resurfacing/ add medians; Air Quality -bike and ped facilities | 2450000 | 2035-2040 |  | 1.17 | 66 | Minor Arterial | STSP-US-13; LCTSP-21b | Incomplete
Main St. (OR 126) | 72nd St. to Springfield UGB | Modify Main St. to a three-lane cross section with sidewalks and bike facilities | ODOT, Springfield | Exempt - Safety- widen lanes/resurfacing/ add medians; Air Quality -bike and ped facilities | 10000000 | 2035-2040 |  | 0.97 | 30 | Other Principal Arterial | US-15 | Incomplete
Randy Pape Beltline Highway | River Road to Coburg Road | Improve facility consistent with the Beltline Highway Facility Plan -- complete components of the project that are not covered by the project on the within 20-years list. | ODOT, Eugene | non-exempt; regionally significant; project of local air quality concern | 685000000 | 2035-2040 |  | 6.39 | 555 | other freeways and expressways | Eugene TSP #B-4 | incomplete
Northwest Expressway | River Road to Irvington Drive | Provide improvements to facilitate vehicular movement along the Northwest Expressway corridor | Eugene, Lane County | non-exempt |  | 2035-2040 |  | 4.45 | 566 | Minor Arterial | Eugene TSP #B-2 | incomplete
30th Ave/McVay Highway/I-5 Interchange | 31st Ave/McVay Highway/I-5 Interchange | Widen 30th Avenue structure over I-5 as well as McVay Highway and Franklin Boulevard ramp terminals to accommodate future multimodal users and motor vehicle capacity and improve safety for all modes. | Lane County, ODOT |  | 65000000 | Beyond 20 years |  |  |  |  | LCTSP-5a | New bridge over I-5 should be a discussion with ODOT; premature at this time. I-5 is an emergency route, but I don't think this bridge has been identified as being seizmically vulnerable. Regarding 30th/McVay capacity, in 2020, OTC approved our alternate mobility target, so implementing this project is not necessary under existing conditions and less of a priority to implement for future conditions. Assumptions would change considerably and this would need to be reevaluated if this area ever becomes incorporated (i.e. Eugene UGB expansion).
30th Ave Exit Ramp | 30th Ave Exit to Gonyea Rd | Remove clover ramp to improve access. (Dependent on implementation of Lane County TSP Project 118) | Lane County |  | 950000 | Beyond 20 years |  |  |  |  | LCTSP-5b | Premature at this time; we don't want to remove the ramps without signal improvements elsewhere.
Green Hill Road | Barger Drive to Airport Road | Construct to major collector standards with two 11' travel lanes and 6' shoulders on both sides. Integrate systemic safety measures. | Lane County, Eugene |  | 2875000 | Beyond 20 years |  |  |  |  | LCTSP-56b
Green Hill Road | Highway 126 to Crow Road | Construct to major collector standards with two 11' travel lanes and 6' shoulders on both sides. Integrate systemic safety measures. | Lane County, Eugene |  | 600000 | Beyond 20 years |  |  |  |  | LCTSP-56c

## Auto Illustrative - Added Freew
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Federal Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Added Freeway Lanes or Major Interchange Improvements
I-5 | @ Willamette River/ Franklin Boulevard Interchange @ Glenwood Interchange | Interchange reconstruction to create one full interchange to improve operations and safety, reconstruct ramps and bridges to modern standards, and provide for 6 lanes on I-5. | ODOT | non-exempt; regionally significant; project of local air quality concern | 45000000 | 2035-2040 |  | 0 | 150 | Urban Interstate |  | This project is not identified in either the Eugene or Springfield TSPs.
I-105 | Washington/ Jefferson Street Bridge | Add lane to 6th Ave. off-ramp | ODOT | non-exempt; regionally significant; project of local air quality concern | 6200000 | 2035-2040 |  | 0.25 | 151 | Urban Interstate |  | This project is not identified in the Eugene TSP.
I-105 | Washington/ Jefferson Street Bridge | Extend third NB lane over bridge to Delta Highway exit ramp | ODOT | non-exempt; regionally significant; project of local air quality concern | 8400000 | 2035-2040 |  | 0.75 | 154 | Urban Interstate |  | This project is not identified in the Eugene TSP.
I-5 | 30th Avenue/McVay Highway I-105 to Highway 58 (Goshen) | Interchange reconstruction to improve operations and safety, reconstruct ramps and bridges to modern standards, and provide for 6 lanes on I-5. | ODOT | non-exempt; regionally significant; project of local air quality concern | 65000000 | 2035-2040 |  | 5.66 | 257 | Urban Interstate | Lane County TSP project 5a, Eugene TSP project B-8.
Eugene-Springfield Highway (OR-126E) at Pioneer Parkway | Pioneer Parkway/ Q Street | Interchange improvements | ODOT | non-exempt; regionally significant; project of local air quality concern | 21700000 | 2035-2040 |  | 0 | 727 | Other Freeways and Expressways | OR126E Expressway Management Plan (2006) | This project is not identified in the Springfield TSP.
Eugene-Springfield Highway (OR-126E) | I-5 to Mohawk Boulevard | Widen to 6 lanes | ODOT | non-exempt; regionally significant; project of local air quality concern | 29000000 | 2035-2040 |  | 2.6 | 728 | Other Freeways and Expressways | OR126E Expressway Management Plan (2006) | This project is not identified in the Springfield TSP.
I-5 | @ City of Coburg interchange (Phase 2) | Interchange improvements | ODOT, Lane County | Outside the PM10 AQMA | 35000000 | 2035-2040 |  | 0 | 1004 | Urban Interstate | LCTSP-27

## Auto Illustrative - Urban Stnds
Name | Geographic Limits | Description | Primary Jurisdiction | AIr Quality Status | Estimated Cost (2020) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Urban Standards
Jasper Road | S. 42nd Street to Springfield UGB | Modify Jasper Road to a three-lane cross-section with sidewalks and bicycle facilities | Lane County, Springfield | Exempt - Safety- widen lanes/resurfacing/ add medians; Air Quality -bike and ped facilities | 6663525 | 2035-2040 |  | 1.01 | 60 | Major Collector | US-12 | Incomplete - clean description to say "bike lanes" instead of "bikelane"
Oakdale Ave | Pheasant Blvd. to Game Farm Road | Modify Oakdale Ave to a two-lane cross-section with sidewalks and bicycle facilities | Springfield | [7 empty] | US-19 | Added part of the latest Springfield 2020 TSP update.
Franklin Blvd | Jenkins Dr to Mill St | Upgrade to urban facility | ODOT | Non-exempt | 6191000 | 2035-2040 |  | 1.2 | 839

## Transit Constrained
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2021) | Estimated Year of Construction (4-Year Window) | Year of Construction Range |  | Length | RTP #
Project Category: Buses and Bus Maintenance
Bus Purchases |  | New & Replacement Buses | Lane Transit District | Non-Exempt | 67790000 | 2021-2025 | 69891490 | 78969422.1871 | - | 1110
Bus Purchases |  | New & Replacement Buses | Lane Transit District | Non-Exempt | 31460000 | 2026-2030 | 37784241.6387 | 42691888.9551 | - | 1110
Bus Purchases |  | New & Replacement Buses | Lane Transit District | Non-Exempt | 55000000 | 2031-2035 | 76949890.7565 | 86944611.0021 | - | 1110
Bus Purchases |  | New & Replacement Buses | Lane Transit District | Non-Exempt | 55000000 | 2036-2040 | 89639893.9431 | 101282869.0532 | - | 1110
Bus Purchases |  | New & Replacement Buses | Lane Transit District | Non-Exempt | 55000000 | 2041-2045 | 104422637.9938 | 117985685.8915 | - | 1110
|  | Project Category Subtotal |  |  | 264250000 |  | 378688154.3322 | 427874477.0889
Project Category: Frequent Transit Network
Enhanced Corridor | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt | 25000000 | 2021-2025 | 29122813.9059 | 32905462.2617 | - | 1117
Enhanced Corridor | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt | 25000000 | 2026-2030 | 33925531.5918 | 38331986.1573 | - | 1117
Enhanced Corridor | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt | 25000000 | 2031-2035 | 39520277.7282 | 44653411.9801 | - | 1117
Enhanced Corridor | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt | 25000000 | 2036-2040 | 46037667.7514 | 52017320.2943 | - | 1117
Bus Rapid Transit (EmX) | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt; Regionally significant | 65000000 | 2021-2025 | 75719316.1552 | 85554201.8804 | - | 1115
Bus Rapid Transit (EmX) | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt; Regionally significant | 65000000 | 2026-2030 | 88206382.1387 | 99663164.0091 | - | 1115
Bus Rapid Transit (EmX) | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt; Regionally significant | 65000000 | 2031-2035 | 102752722.0933 | 116098871.1482 | - | 1115
Bus Rapid Transit (EmX) | TBD - see study corridors map for identifed potential corridors | High Capacity Transit | Lane Transit District | Non-Exempt; Regionally significant | 65000000 | 2036-2040 | 119697936.1538 | 135245032.7651 | - | 1115
|  | Project Category Subtotal |  |  | 360000000 |  | 534982647.5183 | 604469450.4961
Project Category: General Stops and Stations
Passenger Boarding Improvements | Various | Pads, benches, and shelters | Lane Transit District | Exempt - Mass Transit - Construction of small passenger shelters and information kiosks. Other - transportation enhancement activites | 22975000 | 2021-2025 | 26763865.9795 | 30240119.8185 | - | 1130
Passenger Boarding Improvements | Various | Pads, benches, and shelters | Lane Transit District | Exempt - Mass Transit - Construction of small passenger shelters and information kiosks. Other - transportation enhancement activites | 14000000 | 2026-2030 | 18998297.6914 | 21465912.2481 | - | 1130
Passenger Boarding Improvements | Various | Pads, benches, and shelters | Lane Transit District | Exempt - Mass Transit - Construction of small passenger shelters and information kiosks. Other - transportation enhancement activites | 12700000 | 2031-2035 | 20076301.0859 | 22683933.2859 | - | 1130
Passenger Boarding Improvements | Various | Pads, benches, and shelters | Lane Transit District | Exempt - Mass Transit - Construction of small passenger shelters and information kiosks. Other - transportation enhancement activites | 20700000 | 2036-2040 | 38119188.8982 | 43070341.2037 | - | 1130
Passenger Boarding Improvements | Various | Pads, benches, and shelters | Lane Transit District | Exempt - Mass Transit - Construction of small passenger shelters and information kiosks. Other - transportation enhancement activites | 12700000 | 2041-2045 | 27243967.4695 | 30782579.8126 | - | 1130
|  | Project Category Subtotal |  |  | 83075000 |  | 131201621.1245 | 148242886.3688
|  | Financially Constrained Transit Projects |  |  | 707325000 |  | 1044872422.975 | 1180586813.9538

## Transit Illustrative
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2021) | Estimated Year of Construction (4-Year Window) | Year of Construction Range |  | Length | RTP #
Project Category: Frequent Transit Network
Enhanced Corridor | TBD - see study corridors map for identified potential corridors |  | Lane Transit District | Non-Exempt | 25000000 | 2041-2045 | 53629857.2234 | 60595629.5525 | - | 1116
Bus Rapid Transit (EmX) | TBD - see study corridors map for identified potential corridors |  | Lane Transit District | Non-Exempt; Regionally significant project | 65000000 | 2041-2045 | 139437628.7808 | 157548636.8364 | - | 904
| Project Category Subtotal |  |  |  | 90000000 |  | 193067486.0042 | 218144266.3888

## Bike Constrained - woutRd
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Range |  | Length | RTP # | Federal Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Multi-Use Paths Without Road Project
Coburg Loop Phase IV |  | Multi-Use Path | Coburg | Outside PM10 air quality maintenance area | 800000 | 2016-2019 |  |  | 475 | 1005 |  | LCTSP-26?? | From Megan Winner: "The Coburg Loop IV is in process. I believe that it was originally meant to go to Armitage Park. However, the City requested it be moved to industrial way to connect wetland park and because of the costs that it would take to complete the project over and above what was being funded. If this is the same project referred to in Coburg IV then the City of Eugene is managing this project and it is most likely to be completed in the late spring-early summer of 2021. It is in the planning and engineering phase." | From LC: City of Coburg has been leading implementation with MPO funding. I'd like to get a better handle on the status and scope to update documenation for the Lane County Bicycle Master Plan in progress. | Need to check in with the CoE and LC to see who's project this is
McKenzie River Path | 42nd Street to 52nd Street | Construct a new multi-use 12 foot wide path from the existing McKenzie Levee path at 42nd St to 52nd St | Springfield | exempt - Air Quality - bike and ped facilities | 3700000 | 2025-2029 |  |  | 1.55 | 753 | Other urban Freeways and Expressways | PB-32 | Incomplete - applying for Oregon Community Paths Project Refinement grant to do concept planning work.
McKenzie Gateway Path | Extend existing Path to Maple Island Road | Construct a new multi-use 12-foot wide path from the end of the existing Riverbend Hospital path to Maple Island Road | Springfield | exempt - Air Quality - bike and ped facilities | 3000000 | 2030-2034 |  |  | 1.3 | 759 | … | PB-1 | Incomplete
Booth Kelly Road | South 28th Street to South 49th Place | Construct a new multi-use 12-foot wide path from South 28th St to South 49th St | Springfield | exempt - Air Quality - bike and ped facilities | 2817000 | 2020-2024 |  |  | 2.14 | 921 | … | PB-37 | Incomplete - should read "S. 28th"
Glenwood Area Willamette River Path (A) | From end of existing path, east of I-5, to Willamette River bridges | Construct a new multi-use 12-foot wide path from the end of the existing path, east of I-5 to Willamette River bridges | Springfield, Willamalane | exempt - Air Quality - bike and ped facilities | 2500000 | 2020-2024 |  |  | 1.22 | 851 | … | PB-17 | Incomplete
Springfield - Mt. Pisgah Connector | Middle Fork Path to Buford Park Road | Route, Multi-Use Path, Bridge | Willamalane, Lane County, Springfield | exempt - Air Quality - bike and ped facilities | 4423000 | 2030-2034 |  |  | 2.78 | 960 | … |  | Incomplete | Don't see this project in Springfield TSP
New multi-use path | Flamingo Avenue to Gateway Street south of Game Bird Park | Construct a new 12-foot wide multi-use path | Springfield | exempt - Air Quality - bike and ped facilities | 70000 | 2025-2029 |  |  | 0.23 | 711 | … | PB-2 | Incomplete - "Flamingo" not "Flemingo"
Wayside Loop | Manor Drive to Riverbend Path | Construct a new multi-use 12-foot wide path from Wayside Lane/Ann Court to the existing Sacred Heart Medical Center-Riverbend path | Springfield | exempt - Air Quality - bike and ped facilities | 80000 | 2025-2029 |  |  | 0.1 | 759 | … | PB-4 | Incomplete - update name and map visual to match Springfield TSP 2020 update revision.
Anderson Lane | By-Gully path to Centennial Blvd. | Add signing and striping on Anderson St and West Quintalt St for bicycle facilities and construct 12-foot wide multi-use path between Anderson Lane and Quintalt St | Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2030-2034 |  |  | 0.59 | 813 | … | PB-13 | Incomplete
Glenwood Bicycle / Pedestrian Bridge | Downtown Springfield and Glenwood | Build bridge between Downtown Springfield and Glenwood or modify existing Willamette River Bridges | Springfield | exempt - Air Quality - bike and ped facilities | 10300000 | 2020-2024 |  |  | 0.22 | 804 | … | PB-19 | Incomplete
Haul Road | Daisy Street to Booth Kelly Road | Construct a new multi-use 12-foot-wide path in the Haul Raod right-of-way | Springfield | exempt - Air Quality - bike and ped facilities | 326000 | 2020-2024 |  |  | 0.14 | 20 | … | PB-38 | In construction (Daisy St to edge of Woodland Ridge subdivision) - complete by time RTP is adopted.Might need to check and see if this project's entirety is accounted for with current development construction or not. PB-38 is on the Springfield TSP beyond 20-yr list, but clearly it is happening sooner! | Keep or delete
Haul Road Path | South 49th Place to UGB | Construct a new multi-use 12-foot-wide path | Springfield | exempt - Air Quality - bike and ped facilities | 3600000 | 2030-2034 |  |  | 3.32 | 21 | … | PB-46 | Partially in construction - partially complete by time RTP is adopted.
Glenwood Area Willamette River Path (B) | Springfield Bridges to Seavey Loop Road | Multi-Use Path | Springfield | exempt - Air Quality - bike and ped facilities | 2900000 | 2025-2029 |  |  | 1.59 | 854 | … | PB-18 | Incomplete | This description and geographic limit does not match the Springfield TSP.
Fern Ridge West Connector | Royal Street to Fern Ridge Path | Multi-Use Path | Eugene, Lane County | exempt - Air Quality - bike and ped facilities | 125000 | 2020-2024 | 141236 | 159580 | 0.8 | 426 |  | PB-395 | incomplete
Spring Boulevard (B) | Central Boulevard to E. 30th Avenue | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 554000 | 2025-2029 | 729185 | 823896 | 0.22 | 281 | … | PB-211 | incomplete
Avalon Street (A) | Candlelight Drive to N Danebo | Multi-Use Path/Route | Eugene | exempt - Air Quality - bike and ped facilities | 87000 | 2030-2034 | 133395 | 150722 | 0.36 | 403 | … | PB-196 | incomplete
West Bank Path Completion | Formac to Owosso Bridge | Construct new concrete multi-use path for Riverbank trail system | Eugene | exempt - Air Quality - bike and ped facilities | 900000 | 2020-2024 | 1016897 | 1148978 | 0.59 | 556 | … | PB-213 | incomplete
South Bank Path | Autzen Connector to Rail underpass | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 5770000 | 2020-2024 | 6519443 | 7366228 | 0.51 | 169 | … |  | incomplete
E. 30th Avenue Path | Hilyard to Spring | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 2749000 | 2025-2029 | 3618285 | 4088249 | 1.16 | 209 | Minor Arterial | PB-21 | incomplete
W. 7th Avenue Path | W. 5th Avenue to Garfield Street | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 951000 | 2025-2029 | 1251724 | 1414305 | 0.4 | 101 | Other urban Freeways and Expressways | PB-222 | incomplete
I-5 Off-Ramp Path | South Bank Path to Riveriew Street | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 639000 | 2025-2029 | 841064 | 950306 | 0.32 | 189 | Other urban Freeways and Expressways | PB-376 | incomplete
W. Amazon Drive Path | Martin Steet to southern section of W. Amazon Drive | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 709000 | 2020-2024 | 801089 | 905140 | 0.36 | 212 | ... | PB-475 | incomplete
Division Avenue Sidewalk Path | Lone Oak Ave. to Beaver Street | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 701000 | 2025-2029 | 922669 | 1042511 | 0.54 | 512 | Other urban Freeways and Expressways | PB-481 | incomplete
Franklin Boulevard Sidewalk Path | Alder Street to Millrace Park Path | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 273000 | 2025-2029 | 359328 | 405999 | 0.18 | 122 | Other Urban Principle Arterial | PB-508 | incomplete
West Bank Path Extension | Division Avenue (at Beaver Street) to Wilkes Drive | Construct new concrete multi-use path to extend Riverbank path system | Eugene | exempt - Air Quality - bike and ped facilities | 3209000 | 2020-2024 | 3625804 | 4096746 | 1.62 | 564 | Urban Collector | PB-552 | incomplete
Beaver-Wilkes Multi-Use Path | Beaver Street to Wilkes street along Eugene's UGB | Construct a separated multi-use path facility | Lane County |  | 2700000 | [6 empty] | LCTSP-18a | Check ETSP to see if this project matches with any
Beaver Street - Hunsaker Lane | Division Ave to River Road | Construct consistent with Beaver-Hunsunker Corridor Study recommendations | Lane County |  | 9300000 | [6 empty] | LCTSP-18b | Check ETSP to see if this project matches with any
Bob Straub Parkway | 57th Street to Jasper Road | Construct multi-use path on both sides of Bob Straub Parkway | Lane County |  | 3000000 | [6 empty] | LCTSP-21a | Check STSP

## Bike Constrained - wRd
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (2016) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: Multi-Use Paths With Road Project
Anderson Lane | By-Gully path to Centennial Blvd. | Add signing and striping on Anderson St and West Quintalt St for bicycle facilities and construct 12-foot wide multi-use path between Anderson Lane and Quintalt St | Springfield, Lane County | exempt - Air Quality - bike and ped facilities | 90000 | 2030-2034 |  | 0.59 | 813 | … | STSP-PB-13, LCTSP-9 | This project is mentioned on the page Bike Constrained - woutRd. Should it be mentioned again here?
Bob Straub Parkway

## Bike Constrained - onstreet w
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: On-Street Lanes or Routes With Road Project
Laura Street | Old Laura Street to Scotts Glen Drive | Striped Lane | Lane County, Springfield | exempt - Air Quality - bike and ped facilities | $- | 2020-2024 |  | 0.4 | 750 | Urban Collector |  | Complete? Section to north still Incomplete - looks as if the visual on the map is for the section that Lane Co just got funded, but it differs from 750 on the Fiscally Constrained Roadway Projects map? Perhaps the description for this project on this list needs to be adjusted? Is this supposed to have an estimated construction year? | Check back with Lane County's projects
Aspen Street | Menlo Loop to West D Street | Striped Lane | Lane County, Springfield | exempt - Air Quality - bike and ped facilities | $- | 2030-2035 |  | 0.58 | 809 | Minor Collector |  | Incomplete - is this supposed to have an estimated construction year? | Check back with Lane County's projects
42nd Street | Marcola Road to Railroad Tracks | Striped Lane | Springfield | exempt - Air Quality - bike and ped facilities | 6000000 | 2020-2024 |  | 1.1 | 713 | Minor Arterial | R-36 | Incomplete
19th Avenue | Henderson Ave to Franklin Blvd. | Striped Lane | Lane County | exempt - Air Quality - bike and ped facilities | 3500000 | 2025-2029 |  | 0.2 | 861 | Minor Collector | R-18 | Incomplete - this is all Lane Co, please change jurisdiction.Time frame probably needs to be updated. | Check back with Lane County's projects... this is posted in LC, but it is also listed in constrained-urban standards. Should it be located in both sections?
Extend South 48th St to Daisy St | Daisy St and South 48th St | Extend S. 48th St with a two-lane cross-section with a parallel multi-use 12-foot wide path and roundabout intersection treatment at Daisy St and 48th St | Springfield | exempt - Air Quality - bike and ped facilities | 3600000 | 2025-2029 |  | 0.3 | 901 | … | R-39 | Incomplete - this will be a multiuse path on the side of the road instead of a bike lane. Please update to match 2020 TSP update. | This should be moved to the Bike Constrained - woutRd section since this is parallel to the road, correct?
28th Street | Centennial Boulevard to Main Street | Striped Lane | Springfield | exempt - Air Quality - bike and ped facilities | 4300000 | 2025-2029 |  | 0.7 | 909 | Urban Collector | US-5 | Incomplete
35th Street | Olympic Street to Commercial Avenue | Striped Lane | Springfield | exempt - Air Quality - bike and ped facilities | 3600000 | 2035-2040 |  | 0.57 | 918 | Urban Collector | US-8 | Incomplete
Commercial Street | 35th Street to 42nd Street | Striped Lane | Springfield | exempt - Air Quality - bike and ped facilities | 4500000 | 2035-2040 |  | 0.7 | 933 | Urban Collector | US-9 | Incomplete
S. 28th Street | Main St to South F St | Striped Lane | Springfield | exempt - Air Quality - bike and ped facilities | 6000000 | 2025-2029 |  | 0.51 | 945 | Urban Collector | US-6 | Incomplete - update description to multiuse path? | Removed US-7 since it is an illustrative project; Multiuse path not relevant for this since it the geo. limits were mislabelled
21st Street | D Street to Main Street | Striped Lane | Springfield | exempt - Air Quality - bike and ped facilities | 2300000 | 2030-2035 |  | 0.2 | 962 | Minor Collector | US-4 | Incomplete
Bertelsen Road | 18th Avenue to Bailey Hill Road | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 0.6 | 315 | Minor Arterial | PB-45 | incomplete
Bethel Drive | Highway 99 to Roosevelt Blvd | Striped Lane or Route | Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 1.69 | 414 | Minor Collector | PB-61 | incomplete
Bailey Lane | Harlow Road to Willakenzie | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 107000 | 2025-2029 |  | 0.85 | 696 | Minor Collector | PB-131 | incomplete
Wilkes Drive | River Road to River Loop 1 | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 0.93 | 554 | Urban Collector | PB-44 | incomplete
County Farm Road | North-to-South section | Striped lane | Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 0.62 | 631 | Urban Collector | MM-12 | incomplete
W. 11th Avenue | Green Hill Road to Terry Street | Striped Lane | ODOT, Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 1.06 | 333 | Other Urban Freeway and Expressways | MM-14 | incomplete | This project is not currently funded. This section of roadway is included in the OR126: Veneta-Eugene NEPA sudy, which will be completed in 2021.
Fox Hollow Road | Donald Street to Cline Road | Striped Lane, shoulders | Eugene, Lane County | exempt - Air Quality - bike and ped facilities | 68000 | 2030-2034 |  | 0.5 | 245 | Rural Major Collector |  | incomplete
Green Hill Road | Barger Drive to West 11th Avenue | Striped Lane | Lane County, Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 2.27 | 454 | Minor Arterial |  | incomplete
County Farm Road | North-to-South section | Striped lane | Lane County, Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 0.62 | 631 | Urban Collector |  | incomplete
County Farm Road | West-to-East section | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 0.53 | 632 | Urban Collector |  | incomplete
W. 11th Avenue | Green Hill Road to Terry Street | Striped Lane | ODOT, Eugene | exempt - Air Quality - bike and ped facilities | $ - |  |  | 1.06 | 333 | Other Urban Principal Arterial |  | incomplete

## Bike Constrained - onstreet wou
Name | Geographic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: On-Street Lanes or Routes Without Road Project
66th Street | Thurston Road to Main Street | Add bicycle lanes | Springfield | exempt - Air Quality - bike and ped facilities | 25000 | 2020-2024 |  | 0.55 | 12 | Minor Collector | PB-53 | Incomplete
S. 67th Street | Ivy Street to Main Street | Add shared-use signing and striping and construct sidewalks to fill gaps | Springfield | exempt - Air Quality - bike and ped facilities | 160000 | 2025-2029 |  | 0.3 | 92 | Minor Collector | PB-49 | Incomplete
S. 70th Street | Main Street to Ivy Street | Add shared-use signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 50000 | 2025-2029 |  | 0.6 | 94 | Minor Collector | PB-51 | Incomplete
Ivy Street | S. 67th Street to S. 70th Street | Add shared-use signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 20000 | 2030-2034 |  | 0.3 | 99 | Minor Collector | PB-50 | Incomplete
Yolanda Avenue | 23rd Street to 31st Street | Striped Lane | Springfield, Lane County | exempt - Air Quality - bike and ped facilities | 20000 | 2016-2019 |  | 0.8 | 784 | Minor Collector | R-26 | Incomplete - segment in City near schools complete, majority County jurisdiction. Ask County for updated time frame. | Check with LC
5th Street | Centennial Boulevard to A Street | Add bicycle facility signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 50000 | 2020-2024 |  | 0.35 | 806 | Urban Collector | PB-23 | Incomplete - did bicycle wayfinding and sharrows on 4th St as interim alternative route in 2020.
Mill Street | Centennial Boulevard to Main Street | Restripe for bicycle facilities with signing | Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2020-2024 |  | 0.99 | 837 | Urban Collector | PB-20 | Incomplete - funded as part of Mill Street Reconstruct project
Nugget, 15th, 17th, 19th in Glenwood |  | Route | Lane County | exempt - Air Quality - bike and ped facilities | 160000 | 2020-2024 |  | 1.58 | 845 | Minor Collector |  | Incomplete - Lane County jurisdiction
Rainbow Drive | Centennial Boulevard to West D Street | Restripe for bicycle facilities with signing | Springfield | exempt - Air Quality - bike and ped facilities | 60000 | 2020-2024 |  | 0.55 | 848 | Minor Collector | PB-14 | Incomplete
G Street | 5th Street to 28th Street | Add bicycle lanes or route | Springfield | exempt - Air Quality - bike and ped facilities | 75000 | 2020-2024 |  | 1.6 | 899 | … | PB-54 | Incomplete
36th Street | Commercial Street to Main Street | Striped Lane or Route | Springfield | exempt - Air Quality - bike and ped facilities | 3000000 | 2020-2024 |  | 0.3 | 939 | Minor Collector | US-10 | Incomplete - name should be "36th St" not "N." per Springfield street naming conventions.
48th/G/52nd | High Banks Road to Aster Street | Construct a new multi-use 12-foot wide path from High Banks Road to Aster St. | Springfield | exempt - Air Quality - bike and ped facilities | 1600000 | 2025-2029 |  | 1.2 | 6 | Urban Collector | PB-55 | Incomplete - update to match 2020 Springfield TSP update (multi-use path, not bike lanes). Need to update cost estimate also ($1,600,000 in 2017 dollars per TSP Volume 2 cost estimate sheet).
Virginia Ave / Daisy Street | South 32nd St to Bob Straub Parkway | Add bicycle facility signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 130000 | 2020-2024 |  | 2.58 | 903 | Major Collector | PB-36 | In Progress / Partially Complete
Pioneer Parkway | Pioneer Parkway at D, E, and F Streets | Add crosswalks on Pioneer Parkway with signage | Springfield |  | 80000 | 2020-2024 |  |  |  | Major Collector | PB-21
D, E, or F Streets | 5th Street to 28th Street | Add biycle facility signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 190000 | 2020-2024 |  | 2.52 | 805 | Major Collector | PB-24 | Incomplete
Hartman Lane/Don Street | South of Harlow Road to OR 126 | Add signing and striping for bicycle facilities and construct sidewalks to fill gaps | Springfield | exempt - Air Quality - bike and ped facilities | 180000 | 2020-2024 |  | 0.55 | 714 | … | PB-5 | Incomplete
Oakdale Street/Pheasant Street/et al. | Game Farm Road to Gateway Road | Add signing and striping for bicycle facilities | Springfield | exempt - Air Quality - bike and ped facilities | 80000 | 2016-2019 |  | 1.14 | 708 | Minor Arterial | PB-3 | Incomplete
West D | Mill Street to D Street Path | Add bicycle facility signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 10000 | 2020-2024 |  | 0.36 | 817 | Minor Collector | PB-15 | In Progress
West D | Aspen Street to D Street Path | Add bicycle facility signing and striping; construct sidewalks to fill gaps | Springfield | exempt - Air Quality - bike and ped facilities | 190000 | 2025-2029 |  | 0.49 | 816 | Minor Collector | PB-16 | Incomplete
A Street | 5th Street to 10th Street | Restripe for bicycle facilities | Springfield | exempt - Air Quality - bike and ped facilities | 40000 | 2020-2024 |  | 0.35 | 822 | Major Collector | PB-26 | Incomplete
33rd Street | V Street to EWEB Path | Add shared-use signing and striping | Springfield | exempt - Air Quality - bike and ped facilities | 10000 | 2025-2029 |  | 0.18 | 724 | … | PB-30 | Incomplete
Mountaingate Drive | Mountaingate Entrance to Dogwood Street | Add shared-use signing and striping, construct sidewalks and drainage improvements to fill gaps | Springfield | exempt - Air Quality - bike and ped facilities | 260000 | 2030-2024 |  | 0.77 | 27 | Minor Collector | PB-44 | Incomplete
Hayden BridgeWay/Grovedale Drive | Hayden Bridge Way/3rd Street, Hayden Bridge | Add a crosswalk and RRFB | Lane County | exempt - Air Quality - bike and ped facilities | 260000 | 2025-2029 |  | 0.01 | 721 | Major Collector | PB-8 | This is Lane County's - please update jurisdiction to reflect this.
EWEB Path | Path crossings of 2nd Street, 9th Street, 11th Street, Rose Blossom Drive, Debra Street, 15th Street, 33rd Street and 35th Street | Improve path crossings to emphasize path priority and improve safety | Springfield | exempt - Air Quality - bike and ped facilities | 50000 | 2020-2024 |  | 0.76 | 720 | … | PB-9 | Incomplete - please fix end of name (Debra, etc. instead of "?")
2nd Street/Q Street | 2nd Street/Q Street | Add a crosswalk with RRFB | Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2020-2024 |  | 0 | 719 | Urban Collector | PB-10 | Incomplete
5th Street | At Centennial Boulevard | Add bicycle facilities through the intersection | Springfield | exempt - Air Quality - bike and ped facilities | 560000 | 2020-2024 |  | 0 | 820 | Major Collector | PB-22
5th Street | @ D Street | Add bicycle facility signing and striping to improve visiblity | Springfield | exempt - Air Quality - bike and ped facilities | 10000 | 2025-2029 |  | 0 | 821 | Major Collector | PB-25 | Incomplete
Main Street | @ 38th Street | Add a mid-block crosswalk with a RRFB | Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2030-2034 |  | 0 | 923 | Other Urban Fwys & Expressways | PB-34 | Incomplete
Bob Straub Parkway | @ Daisy Street | Add a pedestrian/bicycle signal and crossing, coordinate with Springfield TSP's R-44 | Lane County, Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2020-2024 |  | 0 | 24 | Minor Arterial | PB-43 | Incomplete - Lane County jurisdiction, ask them about timing
Thurston Road | @ 66th Street | Add crosswalk with RRFB | Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2025-2029 |  | 0 | 28 | Urban Collector | PB-47 | Incomplete
Thurston Road | 69th Street | Add crosswalk with RRFB | Springfield | exempt - Air Quality - bike and ped facilities | 90000 | 2025-2029 |  | 0 | 29 | Urban Collector | PB-48 | Incomplete - temporary RRFB currently located here, but permanent project incomplete.
Citywide | Citywide | Install mid-block crossings City-wide with RRFBs | Springfield | exempt - Air Quality - bike and ped facilities | 4400000 | 2025-2029 |  | 0 |  | … | PB-52 | In progress - Centennial Blvd at 13th St, S. 32nd at Agnes Stewart MS, Thurston Rd at 64th St, and 21st at H St installed, standard ball flashers along EWEB path and at S. 42nd/Holly upgraded to RRFBs, Jasper Rd at Dondea and Filbert in design, etc.
Oakway Road | Coburg Road to Cal Young Road | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 2184000 | 2020-2024 |  | 0.96 | 604 | Minor Arterial | PB-391 | incomplete
Cal Young Road | Willakenzie Road to Oakway Road | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 508000 | 2020-2024 |  | 0.22 | 605 | Minor Arterial | PB-392 | incomplete
Willakenzie Road | I-5 Path to Cal Young Road | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 3141000 | 2020-2024 |  | 1.38 | 607 | Urban Collector | PB-393 | incomplete
River Road | Division Avenue to Northwest Expressway | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 4441000 | 2020-2024 |  | 2.49 | 565 | Urban Principal Arterial | PB-526 | incomplete
Garfield Street | Roosevelt Boulevard to W. 6th Avenue | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | 93000 | 2020-2024 |  | 0.68 | 145 | Urban Collector | PB-41 | partial (Roosevelt to 2nd Ave complete)
Lincoln Street | W 5th Ave to W 13th Ave | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 1419000 | 2020-2024 |  | 0.61 | 161 | … | PB-571 | incomplete
Lawrence Street | Cheshire Ave to W 13th Ave | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 152000 | 2020-2024 |  | 1.5 | 160 | … | PB-114 | incomplete
McKinley Street | 5th Avenue to 7th Avenue | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | 26000 | 2020-2024 |  | 0.19 | 163 | Urban Collector |  | incomplete
Mill Street | 10th Avenue to 15th Avenue | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | 91000 | 2020-2024 |  | 0.76 | 166 | … | PB-488 | incomplete
Polk Street | 5th Avenue to 24th Avenue | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | 121000 | 2020-2024 |  | 1.14 | 175 | Urban Collector | PB-523 | incomplete
High Street | Cheshire St to 4th Avenue | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 43000 | 2020-2024 |  | 0.25 | 185 | Minor Arterial | PB-503 | incomplete
High Street | E 6th Avenue to E 19th Avenue | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 2267000 | 2020-2024 |  | 0.99 | 187 | Minor Arterial | PB-18 | incomplete
High Street | E 4th Avenue to E 6th Avenue | Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 16500 | 2020-2024 |  | 0.15 | 186 | Minor Arterial | PB-574 | incomplete
8th Avenue | Lincoln St to E Broadway | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 1221000 | 2020-2024 |  | 0.53 | 162 | Urban Collector | PB-583 | incomplete
E 24th Avenue | Willamette Street to Alder Street | Protected Bike Lane | Eugene | exempt - Air Quality - bike and ped facilities | 1189000 | 2020-2024 |  | 0.52 | 201 | Minor Arterial | PB-589 | incomplete
Throne Drive / Danebo Avenue | Barger Avenue to Royal Avenue | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 139000 | 2020-2024 |  | 1.01 | 417 | Minor Collector | PB-609; PB-73 | incomplete
Golden Gardens | Jessen Drive to Barger Drive | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 62000 | 2020-2024 |  | 0.5 | 451 | … | PB-74 | incomplete
Prairie Road | Maxwell Road to Highway 99 | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | 19000 | 2020-2024 |  | 0.15 | 495 | Minor Arterial | PB-59 | incomplete
Gilham Road | Ashbury to Ayers Road | Striped Lane | Eugene | exempt - Air Quality - bike and ped facilities | 83000 | 2020-2024 |  | 0.61 | 662 | Minor Collector | PB-482 | incomplete
Tandy Turn / Lariat Meadows | Oakway Road to Coburg Road | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 71000 | 2020-2024 |  | 0.48 | 686 | … | PB-126 | incomplete
Valley River Way (A) | Valley River Drive to Valley River Connector | Sidewalk Path | Eugene | exempt - Air Quality - bike and ped facilities | 465000 | 2020-2024 |  | 0.23 | 694 | Urban Collector | PB-55 | incomplete
Van Duyn Road / Bogart Road | Willakenzie Road to Harlow Road | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 107000 | 2020-2024 |  | 0.61 | 698 | Minor Collector | PB-131 | incomplete
Grove Street | Silver Lane to Howard Avenue | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 66000 | 2020-2024 |  | 0.16 0.53 | 515 | Minor Collector | PB-53 | incomplete
Hilliard Lane | N. Park Avenue to W. Bank Trail | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 131000 | 2020-2024 |  | 1.09 | 518 | Minor Collector | PB-163 | incomplete
Horn Lane | Lake Drive to River Road | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 116000 | 2020-2024 |  | 0.75 | 521 | Minor Collector | PB-161 | incomplete
Howard Avenue | River Road to N. Park Avenue | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 120000 | 2020-2024 |  | 0.96 | 524 | Minor Collector | PB-539 | incomplete
Lake Drive / Horn Ln/ N. Park Avenue | Howard Road to Northwest Expressway | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 116000 | 2020-2024 |  | 0.91 | 536 | Minor Collector | PB-159 | incomplete
N. Park Avenue | Maxwell Road to Horn Lane | Bicycle Boulevard | Eugene | exempt - Air Quality - bike and ped facilities | 135000 | 2020-2024 |  | 1.02 | 539 | Minor Collector | PB-157 | incomplete
Franklin Blvd. | Brooklyn to Willamette River | Striped lane or multi-use path | Springfield | Exempt - Air Quality - bike and ped facilities | 34000 | 2020-2024 |  | 0.25 | 807 | Other Urban Principal Arterial |  | Check Springfield TSP for jurisdictional #
McVay Highway (OR99) | I-5 to 30th Ave | Striped Lane | ODOT | Exempt - Air Quality - bike and ped facilities | 96000 | 2020-2024 |  | 0.71 | 834 | Urban Minor Arterial |  | I-5 is parallel to McVay Highway (OR99)? The project description needs to be edited.

## Bike Illustrative - woutRD
Name | Geogrpahic Limits | Description | Primary Jurisdiction | Air Quality Status | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status?
Project Category: Multi-Use Paths Without Road Project
Coburg Loop Path: Armitage Park Connector | McKenzie View Rd. intersection at Coburg Rd. north (most likely) along former rail grade connecting adjacent to Roberts Rd. to Assessors Map 16-03-33-40, Tax Lot 00700 | A 10' wide hardsurface, multiuse path extending approximately one mile between Southern end of Roberts Rd., Coburg and ArmitageCounty Park, Eugene on the McKenzie River | Coburg | Outside PM10 air quality maintenance area | 940000 | 2035-2040 |  | 1.3 | 1001 |  |  |  | These projects should be moved to Bike Constrained - onstreet woutRD since they occur within 20 years, correct?
New multi-use path | South 2nd Street to South B Street | Construct a new multi-use 12-foot wide path from South 2nd St to South B St | Springfield | exempt - Air Quality - bike and ped facilities | 600000 | 2035-2040 |  | 0.16 | 911 |  | PB-28 | Incomplete - adjust limits to match 2020 Springfield TSP amendments
New multi-use path | South 2nd Street to Island Park | Construct a new multi-use 12-foot wide path along the Mill Race | Springfield | exempt - Air Quality - bike and ped facilities | 3100000 | 2035-2040 |  | 0.18 | 912 |  | PB-27 | Incomplete
I-5 Path | Willamette River Area Path to By-Gully Path | Construct a new multi-use 12-foot wide path parallel to I-5 from Willamette River area path/Eastgate Woodlands to the end of the By-Gully Path | Springfield | exempt - Air Quality - bike and ped facilities | - | Beyond 20 years |  | 0.95 | 814 |  | PB-12 | Incomplete
By Gully Path Extension | Pioneer Parkway to 5th Street | Construct a new multi-use 12-foot wide path from the existing By-Gully path at Pioneer Parkway to 5th St | Willamalane, Springfield | exempt - Air Quality - bike and ped facilities | - | Beyond 20 years |  | 0.11 | 812 | … | PB-11
Extend EWEB Trail | Pioneer Parkway to Don St | Construct a new multi-use 12-foot wide path in the EWEB powerline corridor from Pioneer Parkway to Don St with a crossing of Pioneer Parkway and Laura St | Springfield |  |  | Beyond 20 years |  |  |  |  | PB-7
Springfield Christian School Channel Path | Dornoch St to Laura St | Construct a new multi-use 12-foot wide path from Dornoch St to Laura St | Springfield |  |  | Beyond 20 years |  |  |  |  | PB-6
16th Avenue Connector | Fern Ridge Path to Jefferson Street | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 164000 | 2035-2040 |  | 0.09 | 112 |  | PB-448 | incomplete
Augusta Street Path | Laurel Hill Park to 30th Avenue | Multi-Use Path | Eugene | exempt - Air Quality - bike and ped facilities | 1441000 | 2035-2040 |  | 0.79 | 221 |  | PB-242 | incomplete
West Bank Path (B) | Hileman Co. Park to Beltline Highway | Multi-Use Path | Lane County | exempt - Air Quality - bike and ped facilities | 6800000 | 2035-2040 |  | 3.75 | 551
Fern Ridge West Connector | Royal Street to Fern Ridge Path | Multi-Use Path | Eugene, Lane County | exempt - Air Quality - bike and ped facilities | 125000 | 2035-2040 |  | 0.8 | 426 |  | PB-395 | incomplete
Willamette McKenzie Path | Beltline Road to Armitage Park | Multi-Use Path | Eugene, Lane County | exempt - Air Quality - bike and ped facilities | 9000000 | 2035-2040 |  | 4.99 | 699 |  | S-17 | incomplete
Fern Ridge Path #3 | Royal Avenue to Fern Ridge Reservoir | Multi-Use Path | Eugene, Lane County | exempt - Air Quality - bike and ped facilities | 1600000 | 2035-2040 |  | 0.91 | 426 |  |  | incomplete

## Bike Illustrative - withRd
Name | Geographic Limits | Description | Primary Jurisdiction | Estimated Cost (20XX) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)

## Bike Illustrative - onstreet w
Name | Geographic Limits | Description | Primary Jurisdiction | Estimated Cost (2016) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: On-Street Lanes or Routes With Road Project
Division Avenue | Loan Oak to Beaver Street | Striped Lane | Eugene | 701000 | 2035-2040 |  | 0.89 | 512 |  | PB-481 | incomplete
McVay Highway | I-5 to Franklin Boulevard | Striped Lane | Springfield | 203000 | 2035-2040 |  | 1.5 | 833
Franklin Blvd. | Jenkins Drive to Mill St. | Striped Lane | Eugene | 163000 | 2035-2040 |  | 1.2 | 839

## Bike Illustrative onstreet wout
Name | Geographic Limits | Description | Primary Jurisdiction | Estimated Cost (2016) | Estimated Year of Construction (4-Year Window) | Year of Construction Cost Range | Length | RTP # | Functional Class | Jurisdictional Project # | Project Status? (Completed, incomplete, etc.)
Project Category: On-Street Lanes or Routes Without Road Project
Jefferson Street | 5th Avenue to 28th Avenue | Striped Lane | Eugene | 206000 | 2035-2040 |  | 0.89 | 157 |  | PB-51 | incomplete
Washington Street | 5th Avenue to 13th Avenue | Striped Lane | Eugene | 83000 | 2035-2040 |  | 0.53 | 266 |  | PB-50 | incomplete
Portland Street | 24th Avenue to 27th Avenue | Bicycle Boulevard | Eugene | 39000 | 2035-2040 |  | 0.31 | 275 |  | PB-397 | incomplete
Spyglass Drive | Cal Young Road to Oakway Road | Route, Accessway | Eugene | 151000 | 2035-2040 |  | 1 | 684 |  | PB-77; PB-258 | incomplete | Note: This will likely get removed from the TSP - should this be removed from the project list then?